## Tabelle1
ID | Priority | Epic | User Story | COS | Effort (Story Points)
1 |  |  |  | Gummischnallen halten das Case. | 5
2 |  |  | As a user I want to have a case that protects the hardware inside in order not to break it. | Stabiles Case | 0
3 |  |  | As a user I want to add a ride and start tracking my GPS position in order to see the proper data. | Click on a button to see a stacked subview with data displayed. Start and Stop button which cause the data to start/stop being recorded. | 2
4 |  |  | As a user I want to have a smartphone app that is easy to use in order not to be confused. | Well designed app. | 8
5 |  |  | As a user I want to record the track in order to see it in the smartphone app later. | Data transmitted to the app via Bluetooth and displayed in the app | 3
6 |  |  | As a user I want to have my descents listed in the app in order to have a good overview. | See a list of all the recorded tracks in a well designed app. | 2
7 |  |  | As a user I want to see the data of the ride in the app in order to train competitively. | Calculated and displayed in app, gained via device | 8
8 |  |  | As a user I want to compare my rides via the data the device has recorded in order to compare my results. | Red and green overlay over recorded tracks, … | 5
9 |  |  | As a user I want to see currently tracked ride on top of the list in the main view.
10 |  |  | As a user I want to see details of a ride (selected in main view) | Data to be saved and "verarbeitet"
11 |  |  | As a user I want to see the history of different rides on a trail.
|  |  |  | Summe Story Points | 33
Woche | Offene SP |  | SP erst abziehen, wenn User Story beendet
1 | 33