## Tabelle1
Task | Org. Est. | Cur. Est. | Effort | Remain | Responsible
Hardware Prototyp | 10 | 10 | 0 | 10
Software App | 20 | 20 | 0 | 20
Firmware Prototyp | 20 | 20 | 0 | 20
Software Testing | 5 | 5 | 0 | 5