## Tabelle1
Task | Org. Est. | Cur. Est. | Effort | Remain | Responsible
Harware Selection | 3 | 3 | 2 | 1
Hardware Assembly | 2 | 2 | 0 | 2
Hardware Enclosure | 5 | 5 | 0 | 5
Software Technology Selection | 5 | 3 | 3 | 0
Software "Hello World" | 5 | 6 | 2 | 4
Software Coding | 30 | 30 | 0 | 30
Firmware Prototyp | 20 | 20 | 0 | 20
Software Testing | 30 | 30 | 0 | 30
Testing/Shredding | 30 | 30 | 0 | 30