## Tabelle1
Task | Org. Est. | Cur. Est. | Effort | Remain | Responsible
Software Technology Selection | 5 | 3 | 3 | 0 | Max, Alex
Software "Hello World" | 5 | 14 | 14 | 0 | Max, Alex
Software Coding | 30 | 80 | 58 | 22 | Max, Alex
Software Testing | 30 | 30 | 10 | 20 | Max, Alex