## Tabelle1
ID | Priority | Epic | User Story | COS | Effort (Story Points) | Fertig
1 |  |  | As a user I want to add a ride and start tracking my GPS position in order to see the proper data. | Click on a button to see a stacked subview with data displayed. Start and Stop button which cause the data to start/stop being recorded. | 2 | J
2 |  |  | As a user I want to have a smartphone app that is easy to use in order not to be confused. | Well designed app. | 8 | J
3 |  |  | As a user I want to record the track in order to see it in the smartphone app later. | Data displayed in the app | 3 | J
4 |  |  | As a user I want to have my descents listed in the app in order to have a good overview. | See a list of all the recorded tracks in a well designed app. | 2 | J
5 |  |  | As a user I want to see the data of the ride in the app in order to train competitively. | Calculated and displayed in app, gained via device | 8
6 |  |  | As a user I want to compare my rides via the data the device has recorded in order to compare my results. | Red and green overlay over recorded tracks, … | 5
7 |  |  | As a user I want to see currently tracked ride on top of the list in the main view. |  | 1
8 |  |  | As a user I want to see details of a ride (selected in main view) | Data to be saved and "verarbeitet" | 2 | J
|  |  |  | Summe Story Points | 31
Woche | Offene SP |  | SP erst abziehen, wenn User Story beendet
1 | 31
2 | 31
3 | 31
4 | 29
5 | 29
6 | 21
7 | 18
8 | 14