## Tabelle1
Task | Org. Est. | Cur. Est. | Effort | Remain | Responsible
Hardware Selection | 3 | 3 | 2 | 1 | Daniel
Hardware Assembly | 2 | 2 | 0 | 2
Hardware Enclosure | 5 | 5 | 0 | 5
Software Technology Selection | 5 | 3 | 3 | 0 | Max, Alex
Software "Hello World" | 5 | 14 | 14 | 0 | Max, Alex
Software Coding | 30 | 40 | 0 | 40 | Max, Alex
Firmware Prototyp | 20 | 20 | 0 | 20
Software Testing | 30 | 30 | 0 | 30
Testing/Shredding | 30 | 30 | 0 | 30